## Burndown_Sprint1
BurnDowm Sprint 1 Feb 26 - Mar 5
Product backlog | Time estimation (hour) | cumulative | work finish
Requirements Specification Document | 6 | 56 | yes
Order the parts from China | 6 | 50 | yes
Create initial box design | 8 | 44 | yes
Research how to improve streaming quality and performance | 10 | 36 | yes
Design Document | 6 | 26 | yes
Create initial Android App with basic design and no functionality | 20 | 20 | yes
Time Remains (Day) | Hour
| idealBurnDown | HoursComplete
1 | 56 | 56
2 | 48 | 50
3 | 40 | 50
4 | 32 | 50
5 | 24 | 44
6 | 16 | 16
7 | 0 | 0